## Sheet2
Date | No of Hours | Description of work done
2026-01-13 | 2 | finalised research idea for FarmVendor application by defining the core problem and scope.
| 1 | Install the basics development tools: .NET SDK,VS Code, SQL Server LocalDB,Node.js (for React)
2026-01-14 | 4 | Create backend: ASP.NET Core Web API and Tested in browser by resolving multiple installation dependency issues
2026-01-15 |  | Integrated ASP.NET Core Web API (net8.0)
| 4 | Configured SQL Server Local DB (FarmVendorDb)
Implemented ASP.NET Identity
Defined Roles: Farmer and Vendor
JWT authentication
2026-01-17 | 2 | Working endpoints tested on postman (POST /Api/auth/register, POST /Api/auth/login)
2026-01-20 | 0.5 | Project idea re-evaluation with Professor(Madam Priya) and refined research idea
2026-01-21 | 2 | Initial research on existing mobile, web-based applications and background research
2026-01-22 | 2 | Initial Research proposal draft development
2026-01-24 | 2 | Research on React integration with ASP .NET backend
| 2 | Continued Research proposal development
2026-01-25 | 2 | Continued Research proposal development
2026-01-26 | 1 | Finalize research proposal and submission
2026-01-27 | 3 | reviewed submitted proposal and feedback with Professor and
Modifications on data collection strategy
2026-01-29 | 4 | Resolved issue on JWT authentication and protected API access.
Corrected postman authorization configuration
2026-02-02 | 2 | Moved .gitignore to repository root and cleaned tracked artifacts
2026-02-04 | 3 | Initial Farmvendor frontend sketches creation and planned react component structure
Download necessary react dependencies
2026-02-05 | 2 | Resolved errors on installation issues with Node.js and npm.
2026-02-08 | 3 | Completed login.jsx, register.jsx, FarmerDashboard.jsx, App.jsx and dashboard css stylings and modified App.jsx routing
2026-02-09 | 5 | completed VendorDashboard.jsx and modified App.jsx routing
Upload modified proposal on GitHub repository
Updating work log on progress report 1
Initial checking worklog excelsheet on GitHub
Progress report 1 checking on GitHub repository
2026-02-10 | 3 | fixed alignment issues of all interfaces,finaly found root cause in auth.css file which had default paddings and configurations,updated login and registration with 2 panel interface
2026-02-12 |  | in the process of connecting frontend with backend;frontend login connected with backend login
created SQL Server LocalDB database in college pc by using migration files
2026-02-15 | 4 | resolving vite not loading environment error
resolving registering and login user issue
2026-02-17 | 6 | frontend user registration issue sorted : register page used mock mode and pointed to old url
upto now : Role-based authentication Registration + Login Farmer dashboard Vendor dashboard DB persistence JWT working Protected routing
issues:table RelationshipStats has two foreign keys to the same table and sql server blocking that activity;solution : in AppDbContext.cs, add OnModelCreating and change delete behavior to Restriction for AT LEAST 1 FK,drop db completely and recreate again
created MVP schema including Product,DemandRequest,Dispatch,RelationshipStat,__EFMigrationsHistory
Implemented InventoryLot Table
created Real DB data in dashboards
Updated FarmerDashboard with real data from DB
2026-02-18 |  | TO DO : Data generation phase
Implement forecasting module
Optimization model (core research novelty)
Add relationship score tracking
Experiment + evaluation
2026-02-23 |  | add product lot farmer;react form,api:post
2026-02-24 |  | API: POST /api/farmer/inventorylots=>CreateInventoryLotDto,InventoryLotsController
2026-02-28 |  | generated dispatch module front end (updated FarmerDashboard.jsx,dashboard.css)
2026-03-01 |  | generated dispatch module backend (DispatchController.cs,CreateDispatchDTO.cs,)
2026-03-02 |  | sorted issue on create dispatch with select request: solution:dispatchid initialized in back end is different with frontend
sorted issue on updating dispatched items on model submission:solution:demandRequestId id not defined in backend controller farmercontroller.cs
created outlet element for nested pages in requireAuth and RequireRole.jsx
completed farmer product frontend and backend (FarmerProducts.jsx,farmerController.csProductsController.cs,InventoryLotDTO.CS,UpdateInventoryLotDTO.cs)
|  | completed farmer request window both frontend and backend functionality(FarmerController.cs,FarmerDemandRequestRowDto.cs,FarmerRequests.jsx) | submitted
2026-03-03 |  | update vendor dashboard(create dispatch model including filesvendorDashboard.jsx,VendorDemandRequestsController.cs)
fully integrated create demand request modal

## Sheet4
Date | No of Hours | Description of work done
2026-01-13 | 2 | Finalised research idea for FarmVendor application by defining the core problem and scope
| 1 | Installed development tools: .NET SDK, VS Code, SQL Server LocalDB, Node.js (React)
2026-01-14 | 4 | Created backend ASP.NET Core Web API and tested in browser by resolving installation dependency issues
2026-01-15 | 4 | Integrated ASP.NET Core Web API (.NET 8.0)
Configured SQL Server LocalDB (FarmVendorDb)
Implemented ASP.NET Identity
Defined roles: Farmer and Vendor
Implemented JWT authentication
2026-01-17 | 2 | Tested working endpoints on Postman (POST /Api/auth/register, POST /Api/auth/login)
2026-01-20 | 0.5 | Project idea re-evaluation with Professor (Madam Priya) and refined research idea
2026-01-21 | 2 | Initial research on existing mobile and web-based applications and background research
2026-01-22 | 2 | Initial research proposal draft development
2026-01-24 | 2 | Research on React integration with ASP.NET backend
| 2 | Continued research proposal development
2026-01-25 | 2 | Continued research proposal development
2026-01-26 | 1 | Finalised research proposal and submission
2026-01-27 | 3 | Reviewed proposal with professor and applied modifications to data collection strategy
2026-01-29 | 4 | Resolved JWT authentication and protected API access issues
Corrected Postman authorization configuration
2026-02-02 | 2 | Moved .gitignore to repository root and cleaned tracked artifacts
2026-02-04 | 3 | Created frontend sketches and planned React component structure
Installed necessary React dependencies
2026-02-05 | 2 | Resolved Node.js and npm installation issues
2026-02-08 | 4 | Implemented Login.jsx, Register.jsx, FarmerDashboard.jsx, App.jsx and dashboard styling
Modified routing in App.jsx
2026-02-09 | 5 | Implemented VendorDashboard.jsx and updated routing
Uploaded modified proposal to GitHub
Updated worklog for progress report 1
Verified repository contents
2026-02-10 | 5 | Fixed UI alignment issues and corrected auth.css padding problems
Updated login and registration with 2-panel interface
2026-02-12 | 4 | Connected frontend login with backend authentication
Created SQL Server LocalDB database using migrations
2026-02-15 | 5 | Resolved Vite environment loading issues
Fixed registration and login user errors
2026-02-17 | 6 | Fixed frontend registration issue caused by mock mode configuration
Completed role-based authentication, dashboards, DB persistence, JWT and protected routing
Fixed RelationshipStats FK constraint issue and recreated database
Created MVP schema: Product, DemandRequest, Dispatch, RelationshipStat
Implemented InventoryLot table
Added real DB data to dashboards
Updated FarmerDashboard with real DB data
2026-02-18 | 6 | Planned next phase tasks: data generation, forecasting module, optimization model, relationship scoring and evaluation
2026-02-23 | 8 | Implemented Add Product Lot feature (React form + API POST)
Created API endpoint POST /api/farmer/inventorylots using CreateInventoryLotDto and InventoryLotsController
Final Midterm video recording
Final Midterm report completion and submission
2026-02-24 |  | Implemented API endpoint POST /api/farmer/inventorylots using CreateInventoryLotDto and InventoryLotsController
2026-02-28 |  | Developed Dispatch module (frontend) and updated UI styles (FarmerDashboard.jsx, dashboard.css)
2026-03-01 |  | Implemented Dispatch module (backend) (DispatchController.cs, CreateDispatchDto.cs)
2026-03-02 |  | Fixed Create Dispatch - select request issue by aligning backend dispatch initialization and frontend handling
Fixed Dispatched items update issue by adding/returning demandRequestId correctly in FarmerController.cs
Implemented nested routing support by adding Outlet in RequireAuth and RequireRole.jsx
Completed Farmer Products page frontend + backend (FarmerProducts.jsx, FarmerController.cs / ProductsController.cs, InventoryLotDto.cs, UpdateInventoryLotDto.cs)
Completed Farmer Requests page frontend + backend (FarmerController.cs, FarmerDemandRequestRowDto.cs, FarmerRequests.jsx)
|  | Completed Farmer Dispatch page frontend + backend (DispatchRowDto.cs, UpdateDispatchStatusDto.cs, FarmerDispatchController.cs, FarmerDispatch.jsx) | submitted
2026-03-03 | 7 | Implemented inventory lot creation and stock validation logic, enabling farmers to dispatch products based on vendor demand requests.
Developed Vendor Dashboard features including Create Demand Request functionality and integration with backend API endpoints.
Implemented Incoming Dispatches view and Confirm Delivery workflow, updating dispatch delivery status and related demand request statuses.
Debugged and resolved full-stack integration issues including DTO mismatches, dropdown binding errors, missing API response fields, and EF Core query type issues.
Updated Vendor dashboard to support Create Demand Request modal and integrated it with VendorDemandRequestsController.cs and VendorDashboard.jsx.
created export csv back end controller for data extraction
2026-03-07 |  | started with build a simple moving-average demand forecasting module =>later can replace/improve it with ML.NET without changing my whole app
1. Create the DemandForecast model
forecasting baseline module is complete
Implementation Plan : Create Optimization Result Table,
Create Optimization Result Table
DispatchOptimizationService.cs : DispatchOptimizationService.cs
Logic: Read forecast demand Read farmer inventory Match inventory to demand Allocate quantities
Create Optimization API
Relationship Score Tracking
2026-03-08 |  | research on optimization module generation :Based on forecasted demand and available inventory, which farmer should dispatch how much product to which vendor? => Based on forecasted demand and available inventory, which farmer should dispatch how much product to which vendor?
2026-03-09 |  | optimization module
Relationship Score Tracking
store/update relationship score between Farmer ↔ Vendor
update scores automatically when a dispatch becomes:(Delivered,Cancelled)
compute score from measurable factors(On-time delivery rate Fulfillment rate Cancellation rate)
expose API to view scores
add/update:
1. RelationshipStat model
2. RelationshipScoreRowDto
3. RelationshipScoreService
4. RelationshipStatsController
5. integrate score update into:
VendorDispatchesController confirm delivery
optional cancel/update endpoints
TO DO : generate frontend view for below endpoint: GET /api/forecasts POST /api/forecasts/generate GET /api/optimization/plans POST /api/optimization/run GET /api/relationshipstats GET /api/relationshipstats/by-pair?
to do

## Sheet1 (2)
Date | No of Hours | Description of work done
2026-03-03 | 6 | Implemented inventory lot creation and stock validation logic to support dispatch planning from farmer inventory against vendor demand requests.
Developed Vendor Dashboard functionality for Create Demand Request and integrated frontend actions with backend API endpoints.
Implemented Incoming Dispatches view and Confirm Delivery workflow, including updates to dispatch delivery status and related demand request status.
2026-03-05 | 5 | Resolved full-stack integration issues involving DTO mismatches, dropdown binding problems, missing response fields, and EF Core query typing issues.
Updated VendorDashboard.jsx and integrated modal-based demand request creation with VendorDemandRequestsController.cs.
Added backend support for CSV/data extraction to prepare for forecasting and experimental analysis.
2026-03-07 | 6 | Began implementation of a moving-average demand forecasting baseline in .NET as the first forecasting approach for the research module.
Created the DemandForecast model, supporting DTOs, and required database updates for forecast storage.
Completed baseline forecasting workflow and tested forecast generation successfully through API endpoints.
Designed the optimization module structure by defining the optimization result table and dispatch recommendation flow.
Implemented DispatchOptimizationService.cs using greedy baseline allocation logic based on forecast demand and available farmer inventory.
Created optimization API endpoints for generating and retrieving recommended dispatch plans.
2026-03-08 | 3 | Conducted research and design for the optimization component, focusing on demand-driven farmer-to-vendor dispatch decision logic using forecast and inventory data.
Refined the optimization formulation to support the research novelty component of the project.
2026-03-09 | 6 | Implemented the optimization module and connected it with forecast and inventory data to generate recommended dispatch plans.
Implemented relationship score tracking between Farmer and Vendor pairs based on dispatch outcomes.
Added automatic score updates for Delivered and Cancelled dispatch events.
Computed relationship score using measurable factors including on-time delivery rate, fulfillment rate, and cancellation rate.
Exposed backend API endpoints for viewing relationship statistics.
Added and updated files required for relationship scoring, including RelationshipStat, RelationshipScoreRowDto, RelationshipScoreService, and RelationshipStatsController.
Integrated score update logic into VendorDispatchesController confirm delivery flow and outlined remaining frontend analytics views for forecast, optimization, and relationship endpoints.
2026-03-10 | 6 | individual checking
changing research baseline model to ML related model which focus on ML.NET’s forecasting tas
Researched machine learning–based forecasting approaches and identified ML.NET SSA (Singular Spectrum Analysis) time series forecasting as a more suitable ML-driven model for demand prediction.
Updated research direction by replacing the baseline-only approach with an ML-focused forecasting implementation using ML.NET TimeSeries API and refactored the forecasting workflow in DemandForecastService.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data, preparing the implementation structure for MLDemandForecastEngine.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data.
Refactored forecasting architecture to support multiple forecasting models (Moving Average + ML.NET SSA) and updated related models including DemandForecast.cs, GenerateForecastDto.cs, and DemandForecastRowDto.cs
2026-03-11 | 4 | Implemented the ML.NET forecasting engine inside the backend service layer.
Created MLDemandForecastEngine.cs to train ML.NET models using historical demand request quantities stored in the database.
Implemented time-series training pipeline using MLContext and SSA forecasting trainer to predict future vendor demand quantities inside MLDemandForecastEngine.cs
Integrated ML forecast generation into the existing forecasting workflow by updating DemandForecastService.cs so prediction results can be stored in the DemandForecast table
2026-03-12 | 6 | Tested the ML.NET forecasting pipeline using historical demand request data inserted into the database and validated forecasting output.
Verified training data extraction, forecast horizon configuration, and prediction output structure in MLDemandForecastEngine.cs
Added model identification field (ModelName) to distinguish forecast outputs from MovingAverage vs MLNET_SSA models and updated related structures in DemandForecast.cs and DemandForecastRowDto.cs
2026-03-13 | 4 | Developed backend API endpoints to support ML forecasting execution and retrieval through the forecasting module
Implemented API logic in ForecastController.cs for generating ML forecasts and storing prediction results in the database.
Ensured compatibility between backend forecasting APIs and frontend analytics components by updating request/response DTOs such as GenerateForecastDto.cs and DemandForecastRowDto.cs
Developed frontend analytics dashboard for displaying forecasting results and model comparison functionality.
2026-03-16 | 5 | Implemented Vendor Forecast Analytics page in VendorForecast.jsx including forecast generation form and model comparison module between Moving Average and ML.NET models.
Integrated forecasting APIs with React frontend components using secure token-based authentication through forecastApi.js and existing route protection logic
Added forecast visualization charts to the analytics dashboard to represent demand history and forecast trends visually.
Implemented chart component ForecastLineChart.jsx to display historical demand data alongside forecast predictions.
Integrated chart component into both analytics pages VendorForecast.jsx and FarmerForecast.jsx to provide graphical interpretation of forecasting results.
Began implementation of a real-time communication feature between farmers and vendors within the FarmVendor system.
Designed the chat module architecture and developed frontend messaging components FarmerChat.jsx and VendorChat.jsx.
Updated authentication logic in Login.jsx to store userId in localStorage to support message sender identification for chat communication.
Prepared frontend system structure for integrating backend chat APIs and enabling future real-time messaging functionality between farmers and vendors.
Completed Progress report 4 and uploaded to blackboard and checked in to github repository.

## report1
Date | No. of Hours | Description of Work Done
2026-01-13 | 2 | Finalized the research idea for the FarmVendor application by clearly defining the problem statement and project scope.
2026-01-13 | 1 | Installed basic development tools including .NET SDK, Visual Studio Code, and SQL Server LocalDB.
2026-01-14 | 4 | Created a local database and initial React web application. Tested application execution in the browser and resolved multiple dependency installation issues.
2026-01-15 | 4 | Integrated ASP.NET Core Web API (.NET 8.0). Configured SQL Server LocalDB (FarmVendorDb), implemented ASP.NET Identity, defined Farmer and Vendor roles, and set up JWT authentication.
2026-01-17 | 2 | Tested authentication endpoints using Postman, including POST /api/auth/register and POST /api/auth/login.
2026-01-20 | 0.5 | Attended project idea re‑evaluation meeting with instructor (Madam Priya) and refined the research direction.
2026-01-21 | 2 | Conducted initial research on existing mobile and web‑based agricultural supply‑chain applications.
2026-01-22 | 2 | Performed background research and literature review related to demand forecasting and supply‑chain systems.
2026-01-24 | 2 | Conducted research on React integration with ASP.NET backend architecture.
2026-01-25 | 2 | Continued research proposal development, focusing on feature scope and system design.
2026-01-26 | 1 | Finalized the research proposal and prepared it for submission.
2026-01-27 | 3 | Reviewed submitted proposal feedback with instructor and made modifications to the data‑collection and forecasting strategy.
2026-01-29 | 4 | Implemented JWT authorization configuration and secured API endpoints with role‑based access control.
2026-02-02 | 2 | Moved GitHub repository to the root directory and cleaned unused project artifacts.
2026-02-04 | 3 | Created initial frontend sketches for the Farmer Dashboard and planned React component structure. Downloaded and configured required React dependencies.
2026-02-05 | 2 | Resolved installation and configuration issues related to Node.js and npm.
2026-02-08 | 3 | Completed login and registration UI design. Added dashboard CSS styling and modified application routing for Farmer and Vendor dashboards.
2026-02-09 | 3 | Uploaded modified proposal to GitHub. Updated progress report 1, linked working code screenshots, and verified GitHub repository structure.

## final
Date | No. of Hours | Description of Work Done
2026-01-13 | 2 | Finalized the research idea for the FarmVendor application by clearly defining the problem statement and project scope.
2026-01-13 | 1 | Installed basic development tools including .NET SDK, Visual Studio Code, and SQL Server LocalDB.
2026-01-14 | 4 | Created a local database and initial React web application. Tested application execution in the browser and resolved multiple dependency installation issues.
2026-01-15 | 4 | Integrated ASP.NET Core Web API (.NET 8.0). Configured SQL Server LocalDB (FarmVendorDb), implemented ASP.NET Identity, defined Farmer and Vendor roles, and set up JWT authentication.
2026-01-17 | 2 | Tested authentication endpoints using Postman, including POST /api/auth/register and POST /api/auth/login.
2026-01-20 | 0.5 | Attended project idea re‑evaluation meeting with instructor (Madam Priya) and refined the research direction.
2026-01-21 | 2 | Conducted initial research on existing mobile and web‑based agricultural supply‑chain applications.
2026-01-22 | 2 | Performed background research and literature review related to demand forecasting and supply‑chain systems.
2026-01-24 | 2 | Conducted research on React integration with ASP.NET backend architecture.
2026-01-25 | 2 | Continued research proposal development, focusing on feature scope and system design.
2026-01-26 | 1 | Finalized the research proposal and prepared it for submission.
2026-01-27 | 3 | Reviewed submitted proposal feedback with instructor and made modifications to the data‑collection and forecasting strategy.
2026-01-29 | 4 | Implemented JWT authorization configuration and secured API endpoints with role‑based access control.
2026-02-02 | 2 | Moved GitHub repository to the root directory and cleaned unused project artifacts.
2026-02-04 | 3 | Created initial frontend sketches for the Farmer Dashboard and planned React component structure. Downloaded and configured required React dependencies.
2026-02-05 | 2 | Resolved installation and configuration issues related to Node.js and npm.
2026-02-08 | 3 | Completed login and registration UI design. Added dashboard CSS styling and modified application routing for Farmer and Vendor dashboards.
2026-02-09 | 3 | Uploaded modified proposal to GitHub. Updated progress report 1, linked working code screenshots, and verified GitHub repository structure.
2026-02-23 | 8 | Implemented Add Product Lot feature (React form + API POST)
Created API endpoint POST /api/farmer/inventorylots using CreateInventoryLotDto and InventoryLotsController
Final Midterm video recording
Final Midterm report completion and submission
2026-02-24 | 5 | Implemented API endpoint POST /api/farmer/inventorylots using CreateInventoryLotDto and InventoryLotsController
2026-02-28 | 3 | Developed Dispatch module (frontend) and updated UI styles (FarmerDashboard.jsx, dashboard.css)
2026-03-01 | 5 | Implemented Dispatch module (backend) (DispatchController.cs, CreateDispatchDto.cs)
2026-03-02 | 6 | Fixed Create Dispatch - select request issue by aligning backend dispatch initialization and frontend handling
Fixed Dispatched items update issue by adding/returning demandRequestId correctly in FarmerController.cs
Implemented nested routing support by adding Outlet in RequireAuth and RequireRole.jsx
Completed Farmer Products page frontend + backend (FarmerProducts.jsx, FarmerController.cs / ProductsController.cs, InventoryLotDto.cs, UpdateInventoryLotDto.cs)
Completed Farmer Requests page frontend + backend (FarmerController.cs, FarmerDemandRequestRowDto.cs, FarmerRequests.jsx)
Completed Farmer Dispatch page frontend + backend (DispatchRowDto.cs, UpdateDispatchStatusDto.cs, FarmerDispatchController.cs, FarmerDispatch.jsx)
2026-03-03 | 6 | Implemented inventory lot creation and stock validation logic to support dispatch planning from farmer inventory against vendor demand requests.
Developed Vendor Dashboard functionality for Create Demand Request and integrated frontend actions with backend API endpoints.
Implemented Incoming Dispatches view and Confirm Delivery workflow, including updates to dispatch delivery status and related demand request status.
2026-03-05 | 5 | Resolved full-stack integration issues involving DTO mismatches, dropdown binding problems, missing response fields, and EF Core query typing issues.
Updated VendorDashboard.jsx and integrated modal-based demand request creation with VendorDemandRequestsController.cs.
Added backend support for CSV/data extraction to prepare for forecasting and experimental analysis.
2026-03-07 | 6 | Began implementation of a moving-average demand forecasting baseline in .NET as the first forecasting approach for the research module.
Created the DemandForecast model, supporting DTOs, and required database updates for forecast storage.
Completed baseline forecasting workflow and tested forecast generation successfully through API endpoints.
Designed the optimization module structure by defining the optimization result table and dispatch recommendation flow.
Implemented DispatchOptimizationService.cs using greedy baseline allocation logic based on forecast demand and available farmer inventory.
Created optimization API endpoints for generating and retrieving recommended dispatch plans.
2026-03-08 | 3 | Conducted research and design for the optimization component, focusing on demand-driven farmer-to-vendor dispatch decision logic using forecast and inventory data.
Refined the optimization formulation to support the research novelty component of the project.
2026-03-09 | 7 | Implemented the optimization module and connected it with forecast and inventory data to generate recommended dispatch plans.
Implemented relationship score tracking between Farmer and Vendor pairs based on dispatch outcomes.
Added automatic score updates for Delivered and Cancelled dispatch events.
Computed relationship score using measurable factors including on-time delivery rate, fulfillment rate, and cancellation rate.
Exposed backend API endpoints for viewing relationship statistics.
Added and updated files required for relationship scoring, including RelationshipStat, RelationshipScoreRowDto, RelationshipScoreService, and RelationshipStatsController.
Integrated score update logic into VendorDispatchesController confirm delivery flow and outlined remaining frontend analytics views for forecast, optimization, and relationship endpoints.
Developed Progress report3
2026-03-10 | 6 | Individual checking
changing research baseline model to ML related model which focus on ML.NET’s forecasting task
Researched machine learning–based forecasting approaches and identified ML.NET SSA (Singular Spectrum Analysis) time series forecasting as a more suitable ML-driven model for demand prediction.
Updated research direction by replacing the baseline-only approach with an ML-focused forecasting implementation using ML.NET TimeSeries API and refactored the forecasting workflow in DemandForecastService.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data, preparing the implementation structure for MLDemandForecastEngine.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data.
Refactored forecasting architecture to support multiple forecasting models (Moving Average + ML.NET SSA) and updated related models including DemandForecast.cs, GenerateForecastDto.cs, and DemandForecastRowDto.cs
2026-03-11 | 6 | Implemented the ML.NET forecasting engine inside the backend service layer.
Created MLDemandForecastEngine.cs to train ML.NET models using historical demand request quantities stored in the database.
Implemented time-series training pipeline using MLContext and SSA forecasting trainer to predict future vendor demand quantities inside MLDemandForecastEngine.cs
Integrated ML forecast generation into the existing forecasting workflow by updating DemandForecastService.cs so prediction results can be stored in the DemandForecast table
2026-03-12 | 5 | Tested the ML.NET forecasting pipeline using historical demand request data inserted into the database and validated forecasting output.
Verified training data extraction, forecast horizon configuration, and prediction output structure in MLDemandForecastEngine.cs
Added model identification field (ModelName) to distinguish forecast outputs from MovingAverage vs MLNET_SSA models and updated related structures in DemandForecast.cs and DemandForecastRowDto.cs
2026-03-13 | 4 | Developed backend API endpoints to support ML forecasting execution and retrieval through the forecasting module
Implemented API logic in ForecastController.cs for generating ML forecasts and storing prediction results in the database.
Ensured compatibility between backend forecasting APIs and frontend analytics components by updating request/response DTOs such as GenerateForecastDto.cs and DemandForecastRowDto.cs
Developed frontend analytics dashboard for displaying forecasting results and model comparison functionality.
2026-03-16 | 6 | Implemented Vendor Forecast Analytics page in VendorForecast.jsx including forecast generation form and model comparison module between Moving Average and ML.NET models.
Integrated forecasting APIs with React frontend components using secure token-based authentication through forecastApi.js and existing route protection logic
Added forecast visualization charts to the analytics dashboard to represent demand history and forecast trends visually.
Implemented chart component ForecastLineChart.jsx to display historical demand data alongside forecast predictions.
Integrated chart component into both analytics pages VendorForecast.jsx and FarmerForecast.jsx to provide graphical interpretation of forecasting results.
Began implementation of a real-time communication feature between farmers and vendors within the FarmVendor system.
Designed the chat module architecture and developed frontend messaging components FarmerChat.jsx and VendorChat.jsx.
Updated authentication logic in Login.jsx to store userId in localStorage to support message sender identification for chat communication.
Prepared frontend system structure for integrating backend chat APIs and enabling future real-time messaging functionality between farmers and vendors.
Completed Progress report 4 and uploaded to blackboard and checked in to github repository.
2026-03-18 | 4 | Implemented and tested the farmer–vendor chat module in the FarmVendor system. Added chat conversation creation and message flow between farmer and vendor users.
Fixed login-related user identification issues by updating Login.jsx to store userId in localStorage correctly.
Resolved chat database and foreign key issues by verifying valid farmer and vendor IDs from the AspNetUsers table and testing conversation creation successfully.
Fixed SignalR/CORS connection issues by updating backend configuration in Program.cs and retesting real-time chat connection.
Improved chat usability by replacing manual user ID entry with searchable selection of existing farmers and vendors using name/email search. Updated ChatController.cs, chatApi.js, FarmerChat.jsx, and VendorChat.jsx.
Tested the full chat workflow from both farmer and vendor sides, including conversation opening, message display, and sending messages in a more user-friendly interface.
2026-03-19 | 3 | Enhanced user experience of forecasting interface by replacing manual userId inputs with searchable dropdowns for vendor and product selection in FarmerForecast.jsx. Developed backend APIs for vendor and product lookup with search functionality in DemandForecastController.cs (endpoints: /vendors, /products). Updated API integration in forecastApi.js to support dynamic search queries and data fetching. Improved validation handling and request payload structure in forecasting workflow to correctly include vendorId and prevent API errors.
Updated the navigation bar by creating a separate common component file. Refactored FarmerSidebar.jsx, VendorSidebar.jsx, and App.jsx to import the shared component. All related .jsx files were updated to include the new import structure and integrate the sidebar elements.
2026-03-20 | 3 | Implemented ML-based vendor recommendation feature to identify top vendors for dispatching based on forecast demand, inventory availability, and historical request data. Developed backend logic in FarmerRecommendationService.cs and exposed API via FarmerController.cs (/recommended-vendors). Integrated frontend in FarmerDashboard.jsx to display top recommended vendors dynamically.
2026-03-22 | 3 | Populated the system with additional historical demand data to support forecasting experiments and verified that ML.NET SSA forecast rows were generated successfully in the DemandForecast table.
2026-03-23 | 5 | Debugged why recommended vendors and charts were not appearing by checking forecast dates, inventory overlap, API responses, and endpoint usage. Fixed forecasting chart integration by correcting the chart API endpoint in forecastApi.js, updating chart-loading logic to use the selected forecasting model, and refining DemandForecastService.cs chart data retrieval to return recent historical values together with matching forecast values from the selected date onward. Continued testing of farmer-specific recommended vendors and confirmed that recommendation results change based on the logged-in farmer’s inventory and forecast matching data.
Progress report 5 submission
2026-03-24 | 5 | Enhanced forecasting dashboard UI with advanced settings panel including vendor, product, date, model, and horizon selection.
Implemented default parameter auto-loading for vendor, product, and forecast date to improve usability.
Improved error handling for forecast generation and API failures in FarmerForecast.jsx.
2026-03-25 | 4 | Implemented CSV export functionality for forecast results.
Added Export button to forecasting dashboard and generated downloadable CSV file including vendor name, product name, forecast date, quantity, model, and created date.
Ensured removal of internal IDs from export and replaced with user-friendly names.
2026-03-26 | 6 | Upgraded forecast visualization to support multi-vendor comparison charts.
Developed MultiVendorForecastLineChart.jsx to display up to 4 vendors in a single graph with distinct colors and legends.
Integrated vendor selection logic allowing dynamic selection of top vendors from forecast results.
2026-03-27 | 5 | Implemented backend API enhancement for chart data retrieval per vendor and product.
Added filtering logic in DemandForecastController.cs to support vendorId, productId, and forecastDate.
Improved chart API response to include both historical demand and forecast data series.
2026-03-28 | 4 | Enhanced frontend chart rendering logic by fixing dataset mapping and handling missing/null values.
Resolved chart data alignment issues between historical and forecast series.
Improved chart readability with legend labels and consistent formatting.
2026-03-29 | 6 | Implemented vendor filtering logic based on farmer inventory.
Restricted vendors to only those having demand requests matching farmer’s available products.
Updated backend logic in DemandForecastService.cs and FarmerController.cs to support real-world filtering conditions.
2026-03-30 | 5 | Improved forecasting data realism by generating additional historical demand data.
Enhanced SQL scripts using CTE logic to simulate multi-period demand patterns.
Validated ML.NET SSA forecasting output with expanded dataset.
2026-03-31 | 4 | Enhanced dashboard UX by displaying selected vendor name and product name directly on the chart section.
Removed redundant UI elements such as "Available Model Names" for cleaner interface.
Improved layout alignment and readability.
2026-04-01 | 6 | Integrated Unsplash API for product image selection in inventory management.
Implemented image search and selection within Add Product Lot modal.
Stored image metadata (ImageUrl, ImageThumbUrl, PhotographerName) in Product entity and displayed images in UI.
2026-04-02 | 5 | Enhanced product selection UX by displaying images alongside product names in dropdowns.
Improved user experience by allowing visual identification of products.
Added fallback handling for missing images.
2026-04-03 | 6 | Improved real-time chat module stability and authentication handling.
Resolved SignalR WebSocket connection issues caused by missing JWT token.
Updated ChatHub configuration and frontend connection logic to include access token.
2026-04-04 | 5 | Enhanced chat UI by replacing user IDs with display names in conversation lists.
Implemented backend join queries in ChatController.cs to return vendor and farmer names.
Improved conversation selection usability with searchable dropdowns.
2026-04-05 | 4 | Optimized API performance by reducing redundant API calls in forecasting and chat modules.
Implemented caching and minimized repeated fetch requests in React components.
Improved loading times for dashboard and analytics pages.
2026-04-06 | 5 | Performed full system integration testing across all modules including forecasting, dispatch, recommendation, chat, and inventory.
Verified role-based access control for Farmer and Vendor workflows.
Fixed minor bugs related to DTO mismatches and API responses.
2026-04-07 | 4 | Conducted final UI/UX refinements across the application.
Improved dashboard layout to resemble Power BI style with better spacing and card alignment.
Enhanced consistency of buttons, dropdowns, and tables.
2026-04-08 | 6 | Final testing and validation of ML.NET SSA forecasting accuracy and system outputs.
Verified correctness of forecast results, recommendation outputs, and chart visualizations.
Prepared final screenshots, documentation, and report content.
2026-04-09 | 4 | Completed final report writing including architecture diagrams, implemented features, evaluation techniques, and AI usage section.
Prepared appendix with prompt history and finalized all submission materials.

## report4
Date | No of Hours | Description of work done
2026-03-10 | 6 | individual checking
changing research baseline model to ML related model which focus on ML.NET’s forecasting tas
Researched machine learning–based forecasting approaches and identified ML.NET SSA (Singular Spectrum Analysis) time series forecasting as a more suitable ML-driven model for demand prediction.
Updated research direction by replacing the baseline-only approach with an ML-focused forecasting implementation using ML.NET TimeSeries API and refactored the forecasting workflow in DemandForecastService.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data, preparing the implementation structure for MLDemandForecastEngine.cs
Studied ML.NET forecasting pipeline structure including SSA training window, horizon prediction, model retraining, and demand sequence preparation from historical demand request data.
Refactored forecasting architecture to support multiple forecasting models (Moving Average + ML.NET SSA) and updated related models including DemandForecast.cs, GenerateForecastDto.cs, and DemandForecastRowDto.cs
2026-03-11 | 4 | Implemented the ML.NET forecasting engine inside the backend service layer.
Created MLDemandForecastEngine.cs to train ML.NET models using historical demand request quantities stored in the database.
Implemented time-series training pipeline using MLContext and SSA forecasting trainer to predict future vendor demand quantities inside MLDemandForecastEngine.cs
Integrated ML forecast generation into the existing forecasting workflow by updating DemandForecastService.cs so prediction results can be stored in the DemandForecast table
2026-03-12 | 6 | Tested the ML.NET forecasting pipeline using historical demand request data inserted into the database and validated forecasting output.
Verified training data extraction, forecast horizon configuration, and prediction output structure in MLDemandForecastEngine.cs
Added model identification field (ModelName) to distinguish forecast outputs from MovingAverage vs MLNET_SSA models and updated related structures in DemandForecast.cs and DemandForecastRowDto.cs
2026-03-13 | 4 | Developed backend API endpoints to support ML forecasting execution and retrieval through the forecasting module
Implemented API logic in ForecastController.cs for generating ML forecasts and storing prediction results in the database.
Ensured compatibility between backend forecasting APIs and frontend analytics components by updating request/response DTOs such as GenerateForecastDto.cs and DemandForecastRowDto.cs
Developed frontend analytics dashboard for displaying forecasting results and model comparison functionality.
2026-03-16 | 5 | Implemented Vendor Forecast Analytics page in VendorForecast.jsx including forecast generation form and model comparison module between Moving Average and ML.NET models.
Integrated forecasting APIs with React frontend components using secure token-based authentication through forecastApi.js and existing route protection logic
Added forecast visualization charts to the analytics dashboard to represent demand history and forecast trends visually.
Implemented chart component ForecastLineChart.jsx to display historical demand data alongside forecast predictions.
Integrated chart component into both analytics pages VendorForecast.jsx and FarmerForecast.jsx to provide graphical interpretation of forecasting results.
Began implementation of a real-time communication feature between farmers and vendors within the FarmVendor system.
Designed the chat module architecture and developed frontend messaging components FarmerChat.jsx and VendorChat.jsx.
Updated authentication logic in Login.jsx to store userId in localStorage to support message sender identification for chat communication.
Prepared frontend system structure for integrating backend chat APIs and enabling future real-time messaging functionality between farmers and vendors.
Completed Progress report 4 and uploaded to blackboard and checked in to github repository.

## Sheet3
Date | Work Completed | Details / Description
2026-03-03 | Vendor-side functional enhancements | Implemented inventory lot creation and stock validation, enabling farmers to dispatch products based on vendor demand requests. Integrated Create Demand Request UI with backend APIs. Built Incoming Dispatches view and the Confirm Delivery workflow, which updates dispatch and demand request statuses automatically. Fixed multiple integration issues including DTO mismatches, binding errors, missing fields, and EF Core query problems. Added backend CSV/data export features.
2026-03-07 | Baseline demand forecasting module | Developed a simple moving‑average forecasting engine in .NET. Added logic to generate product-level demand predictions and store them in the database for later research and evaluation.
March 7–8 | Dispatch optimization module | Designed and implemented a greedy allocation optimization technique to match farmer inventory with forecasted vendor demand. Created the DispatchOptimizationService, integrated it with inventory and forecast data, and added API endpoints for generating and retrieving optimized dispatch plans.
2026-03-08 | Optimization research & design | Conducted research on allocation strategies to determine how forecasted demand and inventory should drive decisions on which farmer supplies which vendor and in what quantity. Refined the optimization workflow based on analysis.
2026-03-09 | Relationship scoring module | Implemented a scoring model that evaluates farmer–vendor collaboration based on fulfillment rate, on-time delivery, and cancellation rate. Added models, DTOs, and API endpoints for viewing relationship statistics. Integrated automatic score recalculation into the delivery confirmation workflow so that scores update whenever a dispatch is delivered or cancelled.
March 3–9 | Full-stack integration & research preparation | Resolved backend–frontend mismatches across DTOs, route models, and API responses. Ensured that forecasting, optimization, and scoring modules are fully operational for the upcoming experimental evaluation phase. Added database logging and support structures for future analysis.
2026-03-10

## report5
re
| Date | No of Hours | Description of work done
| 2026-03-18 | 4 | Implemented and tested the farmer–vendor chat module in the FarmVendor system. Added chat conversation creation and message flow between farmer and vendor users.
Fixed login-related user identification issues by updating Login.jsx to store userId in localStorage correctly.
Resolved chat database and foreign key issues by verifying valid farmer and vendor IDs from the AspNetUsers table and testing conversation creation successfully.
Fixed SignalR/CORS connection issues by updating backend configuration in Program.cs and retesting real-time chat connection.
Improved chat usability by replacing manual user ID entry with searchable selection of existing farmers and vendors using name/email search. Updated ChatController.cs, chatApi.js, FarmerChat.jsx, and VendorChat.jsx.
Tested the full chat workflow from both farmer and vendor sides, including conversation opening, message display, and sending messages in a more user-friendly interface.
| 2026-03-19 | 3 | Enhanced user experience of forecasting interface by replacing manual userId inputs with searchable dropdowns for vendor and product selection in FarmerForecast.jsx. Developed backend APIs for vendor and product lookup with search functionality in DemandForecastController.cs (endpoints: /vendors, /products). Updated API integration in forecastApi.js to support dynamic search queries and data fetching. Improved validation handling and request payload structure in forecasting workflow to correctly include vendorId and prevent API errors.
|  |  | Updated the navigation bar by creating a separate common component file. Refactored FarmerSidebar.jsx, VendorSidebar.jsx, and App.jsx to import the shared component. All related .jsx files were updated to include the new import structure and integrate the sidebar elements. | correct before submission
| 2026-03-20 | 3 | Implemented ML-based vendor recommendation feature to identify top vendors for dispatching based on forecast demand, inventory availability, and historical request data. Developed backend logic in FarmerRecommendationService.cs and exposed API via FarmerController.cs (/recommended-vendors). Integrated frontend in FarmerDashboard.jsx to display top recommended vendors dynamically.
to do : chack ml forecast for vendor and farmer and charts
add frontend farmer vendor location
connect with aspnetuser table data

## report4 value added
Date | Work Completed | Details / Description
2026-03-10 | Forecasting model research and improvement | Conducted research on machine learning–based forecasting techniques and evaluated the limitations of the baseline Moving Average approach. Identified ML.NET SSA (Singular Spectrum Analysis) Time Series Forecasting as a suitable ML-based approach for predicting vendor demand quantities using historical demand request data.
2026-03-11 | ML forecasting engine implementation | Implemented the MLDemandForecastingEngine.cs module using the ML.NET TimeSeries API. Developed the MLContext pipeline and configured SSA forecasting parameters including training window size, horizon prediction, and historical demand sequence preparation. Integrated the forecasting engine with DemandForecastService.cs to support ML-based demand predictions.
2026-03-12 | Forecasting data validation and testing | Tested the ML.NET forecasting pipeline using historical demand request data stored in the database. Verified training data extraction, demand sequence generation, and forecast output structure. Added model identification logic (ModelName) to support comparison between MovingAverage and MLNET_SSA forecast results.
2026-03-13 | Forecasting API integration | Developed backend API endpoints in DemandForecastController.cs to support generation and retrieval of ML forecasting results. Integrated forecast generation logic with database persistence through EF Core and ensured compatibility with existing forecasting workflows.
| Forecast analytics dashboard development | Implemented frontend analytics pages VendorForecast.jsx and FarmerForecast.jsx to allow users to generate and view forecasting results. Connected frontend components with backend forecasting APIs using secure token-based authentication.
2026-03-16 | Forecast visualization charts | Developed ForecastLineChart.jsx to visualize demand history and forecast predictions. Implemented chart-based representation of historical demand versus forecast results and integrated the chart component into both vendor and farmer analytics dashboards.
| Farmer–Vendor communication module | Designed and implemented a chat system allowing real-time communication between farmers and vendors. Developed backend components including ChatController.cs, ChatService.cs, ChatHub.cs, and database models Conversation.cs and ChatMessage.cs. Implemented frontend chat interfaces FarmerChat.jsx, VendorChat.jsx, and reusable component ChatBox.jsx, enabling users to exchange messages directly within the FarmVendor platform.
| Developed worklog document in professional way | Added required file names accordingly with work done

## report5 value added
Date | Work Completed | Details / Description
2026-03-18 | Chat module integration and enhancement | Independently designed and integrated a real-time farmer–vendor chat system using SignalR within the existing ASP.NET Core + React architecture. Ensured secure communication using JWT-based authentication and proper user identification.
| Debugging and system stabilization | Identified and resolved complex issues related to foreign key constraints, incorrect userId handling, and SignalR CORS/connection errors through debugging and configuration fixes.
| User experience improvement | Enhanced usability by replacing manual ID-based chat initiation with a searchable dropdown using display name and email, making the system more practical and user-friendly.
| Full-stack integration | Successfully connected backend chat APIs, database persistence, and frontend UI components, ensuring end-to-end functionality including conversation creation, message flow, and real-time updates.
| System design improvement | Extended the system architecture to support scalable communication between farmers and vendors, aligning with the project goal of improving coordination and interaction within the supply chain platform.
2026-03-19 | Value added through UI/UX and system integration improvements | Improved overall system usability by eliminating manual ID entry and introducing intuitive search-based selection for vendors and products. Enabled scalable and user-friendly data selection using dynamic backend filtering, enhancing real-world applicability. Strengthened frontend–backend integration by aligning API contracts and validation logic, reducing runtime errors. Contributed to better data accuracy and user adoption by ensuring correct entity selection before forecasting operations.
| code complexity decresed by common navigationbar | Reduced React code complexity by implementing a common navigation bar and eliminated incorrect manual routing paths.
2026-03-20 | Vendor recommendation module implementation | Designed and implemented a data-driven vendor recommendation system using forecasting outputs and historical demand patterns.
Combined ML.NET forecasting results with business logic to rank vendors based on demand, availability, and fulfillment potential.
Enabled decision support for farmers by suggesting optimal vendors for dispatch planning.
Extended system from a transactional platform into an intelligent recommendation-driven system.